## Iterations Routemap
Project Iteration Routemap
Iteration Breakdown Release 1
User Story / Use Case | Type | Size (Large, Medium, Small) | Complexity (High, Medium, Low) | Effort in PDD
Iteration 1 - Elaboration
Component Infrastructure (session data, error logging, persistence framework) | Infrastructure | L | L | 2.25
GUI Infrastructure (Listener standards, error handling and logging, HTTP Request standards, GUI standards) | Infrastructure | L | L | 2.25
Component Support | Infrastructure | S | L | 0.75
Pull skills data | User Story | L | H | 5 | Technology Decisions
Provide organizational resource details | User Story | M | L | 1.5 | System A Integration
Populate Certification Model Data | Infrastructure | L | L | 2.25 | LDAP Connectivity
Login (Initial) | User Story | M | M | 2.5 | WPS Usage
Select Certification (Initial) | User Story | S | M | 1.25 | Workflow Engine
|  |  |  | 17.75 | Start date | End date
|  | Load factor | 3 | 53.25 | 2005-09-12 | 2005-09-23
|  | Number of developers | 5
|  |  | Elapsed time | 10.65 |  | Labor Day
Iteration 2 - Elaboration
Screen Design | UI | M | M | 2.5
Answer Organizational Question Set | User Story | M | L | 1.5
Populate Question Set Data | Infrastructure | M | L | 1.5
Submit Completed Survey | User Story | S | L | 0.75 | Technology Decisions
Flow to Validators | User Story | M | M | 2.5 | Email
Report Technology 'Spike' Solution | Infrastructure | L | H | 5 | Reporting
Determine Global Provider | User Story | M | M | 2.5 | Siebel
Create Worklist | Infrastructure | M | M | 2.5
|  |  |  | 18.75 | Start date | End date
|  | Load factor | 3 | 56.25 | 2005-09-26 | 2005-10-07
|  | Number of developers | 5
|  |  | Elapsed time | 11.25
Iteration 3 - Elaboration
Screen Design | UI | M | M | 2.5
Populate Role to Function Map | Infrastructure | L | H | 5
Answer Certification Question Set | User Story | L | H | 5
Generate PDP | User Story | L | H | 5
Populate PDP Objectives Data | Infrastructure | M | H | 3.5
Release PDP | User Story | M | L | 1.5
|  |  |  | 22.5 | Start date | End date
|  | Load factor | 2.5 | 56.25 | 2005-10-10 | 2005-10-21
|  | Number of developers | 5
|  |  | Elapsed time | 11.25
Iteration 4 - Construction
Attach/Import File | Use Case | M | M | 2.5
Screen Design | UI | M | M | 2.5
Submit Education Validation | Use Case | S | L | 0.75
Amend PDP Objective | User Story | M | L | 1.5
Remove PDP Objective | User Story | M | L | 1.5
Add PDP Objective | User Story | M | L | 1.5
Complete Report Use Cases | Use Case | L | H | 5
Score Submission | User Story | L | M | 3.75
Populate Validator Questions | Infrastructure | M | H | 3.5
Nominate Field Validator | Use Case | S | L | 0.75
|  |  |  | 23.25 | Start date | End date
|  | Load factor | 2.5 | 58.125 | 2005-10-24 | 2005-11-04
|  | Number of developers | 5
|  |  | Elapsed time | 11.625
Iteration 5 - Construction
Accept Program Guidelines | User Story | S | L | 0.75
Demonstrate Partner Certification Progress Status | Infrastructure | M | M | 2.5
Submit Field Validation | Use Case | S | L | 0.75
Submit Legal Validation | Use Case | S | L | 0.75
Submit Customer Success Story | Use Case | S | L | 0.75 | Need to Move Up
Submit Completed PDP | Use Case | S | L | 0.75
Record Progress Against PDP | Use Case | S | L | 0.75
Submit Business Plan | Use Case | S | L | 0.75 | Need to Move Up
Screen Design | UI | M | M | 2.5
Complete Report Use Cases #2 | Use Case | L | H | 5
Complete Report Use Cases #3 | Use Case | L | H | 5
Submit Case for Vote | Use Case | S | L | 0.75
Grant Certification | User Story | S | L | 0.75
|  |  |  | 21.75 | Start date | End date
|  | Load factor | 2.5 | 54.375 | 2005-11-07 | 2005-11-18
|  | Number of developers | 5
|  |  | Elapsed time | 10.875
Iteration 6 - Construction
Complete User Help | Use Case | L | L | 2.25
Complete Report Use Cases #4 | Use Case | L | M | 3.75
System Test |  | L | H | 5
Defect Correction |  | L | H | 5
|  |  |  | 16 | Start date | End date
|  | Load factor | 2 | 32 | 2005-11-21 | 2005-12-02
|  | Number of developers | 5
|  |  | Elapsed time | 6.4
Iteration 7 - Transition
Integration Test
Defect Correction
|  |  |  | 0 | Start date | End date
|  | Load factor | 2 | 0 | 2005-12-05 | 2005-12-16
|  | Number of developers | 5
|  |  | Elapsed time | 0
Iteration 8 - Transition
UAT
Code Freeze / Deploy
|  |  |  | 0 | Start date | End date
|  | Load factor | 2 | 0 | 2005-12-19 | 2005-12-30
|  | Number of developers | 5
|  |  | Elapsed time | 0
Note on A51: BMC Image: This includes 3 Browse stories and 1 Answer Validator questions
Note on A57: BMC Image: Includes populate data for three different validator question sets
Note on E5: Bryan Campbell: Perfect Development Days
This sheet is an example (although based on real data from a previous project I managed). More details can be found on the Instructions Tab.
Identifying the 'Release' the iterations are supporting helps communicate that there will be future releases that will support additional requirements
Note: the different 'types' of work effort. Infrastructure/UI/User Story. Each type is important to support the complete requirement set of the system.
Identifying the technology decisions that the project needs to make are important not only to 'de-risk' the project but to communicate to other stakeholders when they need to be involved. A Technology Office is often very interested in participating in these decisions. Remember, if a decision can't be made it typically means your project's delivery date is at risk.
The Load Factor reflects assumptions on 'overhead' for the project that affect the Perfect Development Day estimates for completing work. Over time Load Factor is reduced but typically never reaches 1 and is never negative.
If the elapsed time exceeds the length of your iteration you should try and reduce the amount of work scheduled .
When selecting an iteration length base the decision on the time it will take to demonstrate tangible units of business value. You can click here to get more details on selecting the correct itreation length.
Don't forget to identify holidays!.

## Instructions
The Iteration Route Map
The Iteration Route Map is a tool that identifies what functionality will be delivered in each iteration of a project. As the name suggests it acts as a map that project stakeholders can reference in order to anticipate how the application will develop throughout its lifecycle. The Iteration Route Map is primarily used by the architect and development team to manage analysis and design and implementation activities throughout the project. However, the route map is also an important tool for other project stakeholders to reference. Quality Assurance can use the tool to understand what functionality will be available for testing at the completion of each iteration. Support groups such as Database Administrators and IT Operations can use the route map to anticipate when they will need to provide physical data models or infrastructure. The Project Manager uses the Iteration Route Map to develop a project plan that can be used to coordinate the activities of all effort across the disciplines in the project.
The Iteration Routemap is developed from the requirements gathered during the Inception Phase of a project. It is intended to break the development effort into a series of fixed timeframe deliverables each of which incrementally builds upon the results of the previous iteration. When developing the route map a number of inputs are used. The Use cases and their User Stories developed during the Inception phase (which explains why as much of an effort as possible is made to capture all of the use cases during Inception even though they might not be at significantly detailed level), the Class Diagram/Object Model (which, although probably at a very high level and which will probably change change during the Elaboration phase, provides a high level domain view of the class packages for the system), the User Interface Prototype (which shows the screen flow and inputs required for the system) and finally the Software Requirements Specifications (which should document the non-functional requirements for the application and which features are expected in different versions).
As mentioned, the Iteration Route Map is focused on two primary disciplines: Analysis and Design and Implementation. Project implementers can not develop software for items that have not been designed so it is important to balance the routemap in a way that the architect and designer of the project can provide enough design artifacts that the implementers can actually implement what is required. Overtime, however, analysis and design should get ahead of the implementers and in the latter iterations of the project there should be less emphasis on design and more emphasis on testing and deployment.
The first draft of the Iteration Route Map identifies the use cases and other components that will be developed for the system and classifies these in terms of their size and complexity. Three general categories are used: High, Medium or Low for Complexity and Large, Medium and Small for Size. The classifications should be assigned jointly by the architect and the lead developer or possibly the entire engineering and development teams. A weighting is then applied to each of these to components to determine an estimate of development effort, the initial estimate is developed using the concept of Perfect Engineering Days (PED). PEDs reflect a fully productive day of development, no distractions, no meetings, no coffee/smoke breaks, just perfect programming time. These PEDs are then increased by a Load Factor which reflects not only these typical productivity reducers but also includes challenges associated with supporting a particular programming language (for example Visual Basic 6.0 which does not support inheiritance). Development productivity should improve over time (as developers become more familiar with the domain and the team). Items that are both Large and highly Complex are probably good candidates for early iterations as they probably reflect the highest risk items or the most architecturally significant.
Developing the Iteration Route Map is an important element within the development of an application. It requires the skills of an experienced architect to coordinate, ideally the same person who worked on the Inception deliverables of the project. The iteration route map is only a tool to help assess the correct structuring of the development effort of a project. It must be continually revisited throughout the project iteration schedule (as it is possible that some functionality identified within an iteration might be deferred if the development team is unable to complete it by the end of the iteration). In addition, requirements changes might also change assumptions within the routemap. Finally, the weighting factors and the grouping of functionality requires a skilled architect and Lead Developer to assess how long development will take and what functionality has dependencies on other application components.
The Iteration Route Map uses some suggested guidelines which can be easily modified within the template. It is important to review these guidelines to ensure they support the environment of your project as each project is different. At the end of each iteration review the estimates and refine them for the next iteration.
Type: This category simply reflects the type of work that has been used to determine an estimate of effort. Any type of work can be entered into the spreadsheet and for the purposes of the template you will see Use Cases, Infrastructure and CRUDs.
Load Factor: The load factor reflects the productivity of the project and is typically between 2 and 5. 5 reflects a programming language that is either new to the development team or difficult to work with (such as Visual Basic 4/5 within an object oriented development environment). 2 is usually only achieved when the development team has been working on a project for an extended period of time, usually near the latter iterations of the project (when development complexity should be lower). At some point projects would probably get to a load factor of 1 but typically the project ends before this occurs or other variables (such as turnover, vacation etc.) prevent it from happening.
PEDs: Work on a particular use case, class or infrastructure component shouldn't be greater than 5 PEDs. You can adjust the weightings of the Size and Complexity of the templates on the Lookups tabs in the spreadsheet, however, the formula caps the maximum amount of effort at 5 days. If a user story is greater than five days of effort you should examine whether it can be decomposed into smaller stories. 5 PEDs are a good limit to the amount of functionality that should be estimated since effort greater than one week introduces larger potential variances which can have significant impacts on the project schedule. The total effort in PEDs is multiplied by the Load Factor (above) to provide an estimate of ‘real time’ required to complete the iteration. This is divided by the number of Developers in an iteration to yield an Elapsed Time. For a project with four week iterations, the elapsed time should not exceed 21 days.
Start and End Dates: The duration of an iteration should be consistent throughout the project lifecycle. This consistency is important as it allows the route map to more accurately reflect productivity over time (since the standard iteration length provides a benchmark for comparison). More importantly though, it provides a consistent milestone for the project stakeholders to gauge progress and a 'cadence' like drumbeat to measure progress. Ensure that the work within an iteration does not 'stretch' the team as it will mean a significant struggle when the iteration gets closer to the end date and this might lead to the deferment of functionality to another iteration or a poorly designed and tested iteration.
The final comment about the Route Map is to be aware that the estimates reflect 'engineering' estimates which still require validation from the developers themselves. Overtime the engineering team and the development team should be closely aligned but initially it is important to allow the developers an opportunity to develop their own estimates for each iteration. This ensures greater buy-in on their ability to deliver within the iteration timelines. Part of the route map estimating is also intended to identify what the engineering team is capable of analyzing and designing in a given iteration. Remember the developers need good design documents to develop good code, that means use cases, an object model, UI screens, data model and supporting UML artifacts (activity, sequence and collaboration diagrams).
Bryan Campbell
bryan@bryancampbell.com
281-620-3038
www.bryancampbell.com

## Lookups
Lookup Tables for Effort Calculations
Size
L | 3
M | 2
S | 1
Complexity
H | 1.75
M | 1.25
L | 0.75